| Goals, Objectives, Leads & Partners, and Proposed Completion Dates |  |  |  |  | Relationship to RMAC Priorities |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Lead RMAC Member(s) & Affiliates | Lead(s) & Proposed Partner(s) | Estimated Completion | Status | I – Advise the Board & state agencies | II – Education & Workforce Development | III – Monitor & address range issues | IV – CDFA Weeds Programs |
| GOAL 1. Promote appropriate prescribed grazing practices for fuels management, soil health, riparian restoration, biodiversity protection and enhancement, and other ecosystem services. |  |  |  |  |  |  |  |  |
| 1a. Develop standard template(s)/form(s) with accompanying guidance document for constructing grazing agreements and grazing management plans for use by state agencies. | - Bart Cremers - Rich Ross - Dr. Paul Starrs - Dr. Kristina Wolf | - SLGLLM - UCCE/UC ANR - USFS - CAL FIRE - DGS - CDFW - JDSF - Others | 06/2024 | In process of being finalized by summer ‘24 | X |  | X |  |
| 1b. Establish appropriate guidance for grazing on California rangelands, with an emphasis on state-managed lands. | - Lance Criley - Andrée Soares - Cole Bush - Dr. Paul Starrs - Dr. Stephanie Larson - Dr. Kristina Wolf - Roxanne Foss | - RMAC - UCCE/UC ANR - UCB - UCD - CPSLO - CWGA - CCA | 12/2024 |  | X |  | X |  |

| Goals, Objectives, Leads & Partners, and Proposed Completion Dates |  |  |  |  | Relationship to RMAC Priorities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Lead RMAC Member(s) & Affiliates | Lead(s) & Proposed Partner(s) | Estimated Completion | Status | I – Advise the Board & state agencies | II – Education & Workforce Development | III – Monitor & address range issues |  | IV – CDFA Weeds Programs |  |
| GOAL 2. Support workforce development for CRMs and increase collaboration and joint educational opportunities for RPFs and CRMs. |  |  |  |  |  |  |  |  |  |  |
| 2a. Establish an RMAC subcommittee to develop relationships with the CLFA and the CRM Panel to establish joint CRM-RPF annual fuels management training. | - Dr. Marc Horney - Bart Cremers - Dr. Kristina Wolf - Matthew Shapero - David Lile | - RMAC - CLFA - Cal-Pac SRM CRM Panel | 10/2024 | Formed – goal to produce Oak Woodland workshop ~Oct ‘24 |  | X |  | X |  |  |
| 2b. Coordinate CRM and RPF requirements and exam contents where appropriate. | - Dr. Marc Horney - Bart Cremers | - RMAC - OPFR - Cal-Pac SRM CRM Panel | Ongoing |  |  | X |  |  |  |  |
| 2c. Promote existing efforts to develop a statewide training program for potential CRMs. | - Dr. Marc Horney - Dr. Susan Marshall | - RMAC - OPFR - Cal-Pac SRM CRM Panel | Ongoing | Ongoing in 2024 |  | X |  |  |  |  |
| 2d. Invite experts to discuss state requirements for planning and conducting prescribed burns as a CAL FIRE employee or private “burn boss” at a public RMAC meeting. | - Dr. Kristina Wolf - Lenya Quinn-Davidson | - RMAC - CAL FIRE - UCCE/UCANR - PBAs | 10/2024 | No progress |  | X |  |  |  |  |
| 2e. Meet with CRM Panel and Cal-Pac SRM leadership to discuss other methods of promoting CRM utilization and/or further development of the program. | - Dr. Marc Horney - Dr. Stephanie Larson - Dr. Kristina Wolf - Dr. Susan Marshall - Bre Owens | - RMAC - Cal-Pac SRM CRM Panel | 09/2024 | Invite to 2024 fall mtg |  | X |  |  |  |  |

| Goals, Objectives, Leads & Partners, and Proposed Completion Dates |  |  |  |  | Relationship to RMAC Priorities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Lead RMAC Member(s) & Affiliates | Lead(s) & Proposed Partner(s) | Estimated Completion | Status | I – Advise the Board & state agencies | II – Education & Workforce Development | III – Monitor & address range issues |  | IV – CDFA Weeds Programs |  |
| GOAL 3. Develop educational opportunities and outreach for prescribed herbivory, fuel reduction methods integrating prescribed herbivory, and rangeland resource management in general. |  |  |  |  |  |  |  |  |  |  |
| 3a. Coordinate with state agencies and major public landowners to facilitate an inventory of existing land management plans and a system for periodic reporting of range management activities. | - Dr. Stephanie Larson - Dr. Marc Horney - Dr. Kristina Wolf | - RMAC - Various state agencies | Ongoing | No progress | X |  |  | X |  |  |
| 3b. Conduct and promote a collaborative annual educational workshop series on livestock impacts on native plant and animal species. | - Joel Kramer - Cole Bush - Dr. Marc Horney - Dr. Stephanie Larson - Bart Cremers - Dr. Kristina Wolf | - RMAC - UCCE/UC ANR - NRCS - CAL FIRE - BLM - CDFW | Ongoing in 2024 | Completed in 2023; new planning started for 2024 | X | X |  | X |  |  |
| 3c. Develop or approve informational publications and technical guidance for public/agency use. | - Dr. Stephanie Larson - Cole Bush - Joel Kramer - Andrée Soares - Dr. Paul Starrs | - RMAC - CWGA TGC - CA FSC | Ongoing, Factsheet – vote on Board approval (03/24); White paper and Technical Guide (08/24) | Rx herbivory sheet Jan ’23; White paper/tech guidance drafts ~ Summer ‘24 | X | X |  | X |  |  |

| Goals, Objectives, Leads & Partners, and Proposed Completion Dates |  |  |  |  |  | Relationship to RMAC Priorities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective |  | Lead RMAC Member(s)& Affiliates | Lead(s) & Proposed Partner(s) | Estimated Completion | Status | I – Advise the Board & state agencies | II – Education & Workforce Development | III – Monitor & address range issues |  | IV – CDFA Weeds Programs |  |
| GOAL 4. Increase collaborations with advised and related agencies, Native American tribes, and other administrative bodies, and solicit and prioritize current synergistic California rangeland resource priorities |  |  |  |  |  |  |  |  |  |  |  |
| 4a. Regularly solicit requests for investigations of rangeland management topics and extend invitations for periodic public reports on activities and issues. | - RMAC members - Dr. Kristina Wolf |  | - RMAC - Board - Advised agencies (CDFA, CalEPA, CNRA) | Ongoing | Ongoing | X |  |  | X |  |  |
| 4b. Where appropriate, initiate proof-of-concept projects or small-scale collaborative investigations utilizing CDFA mandates under the FAC 7271 and 7273 | - Joel Kramer |  | - RMAC - CDFA - RCD | 05/2023 | No progress |  |  |  | X |  | X |
| Key: BLM = Bureau of Land Management; Board = CA State Board of Forestry and Fire Protection; CA = California; FSC = CA Fire Science Consortium; CalEPA = CA Environmental Protection Agency; CAL FIRE = Department of Forestry and Fire Protection; Cal-Pac SRM = CA Pacific Section of the Society for Range Management; CCA = California Cattlemen’s Association; CCRC = Central Coast Rangeland Coalition; CRCC = CA Rangeland Conservation Coalition; CDFW = CA Department of Fish & Wildlife; CFBF = CA Farm Bureau; CLFA = CA Licensed Foresters Association; CNRA = CA Natural Resources Agency; CDFA = CA Department of Food & Agriculture; CPSLO = CA Polytechnic State University, San Luis Obispo; CRM = Certified Rangeland Manager; CRT = CA Rangeland Trust; CWGA = CA Wool Growers Association; DWR = CA Department of Water Resources; DGS = CA Department of General Services; JDSF = Jackson Demonstration State Forest; NRCS = Natural Resources Conservation Service; OPRF = Office of the Professional Forester Registration; PBA = Prescribed Burn Association; RCD = Resource Conservation District; RPF = Registered Professional Forester; RMAC = Rangeland Management Advisory Committee; RWQB = Regional Water Quality Board ; SLGLLM = State Lands Grazing License & Land Management, a subcommittee of the RMAC; SWRCB = State Water Resources Control Board; TGC = Targeted Grazing Committee; UC ANR = University of CA Division of Agriculture and Natural Resources; UCB = University of CA, Berkeley; UCCE = University of CA Cooperative Extension (UC ANR); UCD = University of CA, Davis; UC NRS = University of CA Natural Reserve System; USFS = United States Forest Service. |  |  |  |  |  |  |  |  |  |  |  |