California Urban and Community Forestry Inflation Reduction Act Grant

Supplemental Grant Guidelines Manual

Federal Assistance Listing:

10.727 IRA Urban & Community Forestry

Effective Date: August 2, 2023

California Department of Forestry and Fire Protection

This page intentionally left blank.

Table of Contents

Overview	3

Authority and Program Purpose	4

Purpose of the Grant Management Procedures Manual	4

General Responsibilities	4

Urban and Community Forestry Program	4

Grant Recipients	4

Recipient Resources	4

Prior Approval Required	5

Project Management	5

Compliance with Federal Requirements	6

Minimum Program Requirements	6

Allowable Costs	6

Unallowable Costs	8

Direct and Indirect Costs	8

Indirect Cost Rate	8

Charging Direct and Indirect Costs Consistently	9

Scope of Work Revisions	9

Line Item Shift Requests	10

Notification of Problems and Delays	11

Program Income	11

Cost Share	12

Timekeeping Requirements	12

Travel	12

Domestic Tavel	12

Ground Transportation	14

Parking	14

Air Travel	14

Contractors/Consultants	15

Competitive Process	15

Noncompetitive Procurement	15

Written Agreement	15

Compensation	16

Contractor/Consultant Invoices	17

Equipment	17

Publicity and Acknowledgment	17

Publicity	18

Acknowledgment of Support	18

Logo Usage	18

Payment Methods	19

Advance Payments	19

Reimbursement Payments	20

Invoices	20

Completing an Invoice	21

Supporting Documentation	22

Reporting Requirements	22

Progress and Final Reports	22

Progress Reports	22

Remaining Funds Reporting	24

Six Months Prior to Project Completion	25

Three Months Prior to Project Completion	25

Single Audit Requirements	25

Compliance and Remedies for Noncompliance	25

Compliance Reviews	25

Remedies for Noncompliance	26

Additional Conditions	26

Termination of Grant Agreement	26

Loss of Funding	27

Closeout	27

Property Management and Disposition	27

Intellectual Property	27

Special Purpose Equipment	28

Record Retention	28

# Overview

## Authority and Program Purpose

The Urban and Community Forestry Inflation Reduction Act (UCF IRA) grant is authorized by the Inflation Reduction Action of 2022, Public Law No: 117-169. Subtitle D, Sec. 23003 (a) (2) which provides for multiyear, programmatic, competitive grants for tree planting and related activities through the Urban and Community Forestry Assistance program established under section 9(c) of the Cooperative Forestry Assistance Act Of 1978 (16 U.S.C. 2105(c)).

The purpose of the UCF IRA grant is to substantially invest in the long-term growth and development of state and local urban and community forestry programs to support:

- increased and equitable access to urban tree canopy and associated human health, environmental and economic benefits in disadvantaged communities,

- broadened community engagement in local urban forest planning,

- improved community and urban forest resilience to climate change, extreme heat, forest pests and diseases, and storm events through best management and maintenance practices

- increased resilience to climate change

## Purpose of the Grant Management Procedures Manual

The UCF IRA grant management procedures manual is designed to provide direction to Grant Recipients (Recipients) for the successful management of UCF IRA grant federally funded projects. This manual identifies the roles and responsibilities of all parties and describes the processes and procedures required by the terms and conditions in the Grant Agreement.

## General Responsibilities

### Urban and Community Forestry Program

The California Department of Forestry and Fire Protection (CAL FIRE), Urban and Community Forestry (UCF) Program manages the UCF IRA Grant Agreements and ensures Recipients are compliant with applicable federal regulations and requirements and grant terms and conditions. The CAL FIRE UCF Program also provides Recipients with technical assistance throughout the Grant Agreement term.

### Grant Recipients

Recipients implement the Grant Agreement scope of work and ensure all project activities, including contractor/consultant activities, comply with applicable federal regulations and requirements and grant terms and conditions.

## Recipient Resources

Additional resources can be found on the CAL FIRE UCF Program website and the CAL FIRE UCF Hub Site.

# Prior Approval Required

Prior approval is required from the CAL FIRE UCF Program, and in some instances the U.S. Department of Agriculture (USDA) Forest Service, for the following:

- Revision of the scope of work, objectives, work plan, activities, milestones, dates, or deliverables

- Budget changes

- Budget line-item shifts in excess of 10% of the budget category (ex: Salaries and Wages, Employee Benefits, Contractual, Travel, Supplies, Other Costs, Indirect Costs)

- Travel costs not authorized in the grant agreement

- Contracting or obtaining the services of a third party

- Contractor/consultant rates in excess of fair market price

- Fixed amount/flat rate contracts

- Subawarding funds

- Concrete/asphalt removal or installation

- Safety fencing or other temporary installations

- Participation support costs/stipends

- Change in Recipient organization or key personnel

- Absence of key personnel, or a reduction of key personnel time committed to the project of 25 percent or greater

- Change or addition of personnel related to administrative and clerical staff salaries

- Revision to goals and/or subgoals

- Changes to the use of Program Income (if applicable)

The information required for a request for approval varies according to the type of approval sought. Contact your assigned Forester or Grant Administrator for the information required for your situation.

Failure to obtain prior approval may result in costs being deemed unallowable and requests for reimbursement being denied.

# Project Management

## Compliance with Federal Requirements

Guidance for federal awards is published in the Code of Federal Regulations (CFR). The CFR is accessible through the Electronic Code of Federal Regulations at www.ecfr.gov.

Grant funds awarded to state, local, and tribal governments; public and private colleges and universities; and non-profit organizations are subject to the Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards contained in 2 CFR part 200 and 2 CFR part 400.

Grant funds awarded to federal government entities are subject to the Uniform Administrative Requirements and Cost Principles for Federal Awards contained in 2 CFR part 200 and 2 CFR part 400.

Grant funds awarded to for-profit organizations are subject to the Uniform Administrative Requirements contained in 2 CFR part 200 and 2 CFR part 400, and the Cost Principles contained in the Federal Acquisition Regulation (FAR) Subpart 31.2, Contracts with Commercial Organizations, codified at 48 CFR 31.2.

Recipients are responsible for the consistent application of federal regulations to the UCF IRA grant funds. Recipients are responsible for ensuring their contractors/consultants comply with federal regulations.

## Minimum Program Requirements

All UCF IRA grants must advance the development of sustainable and accessible urban and community forests in California. Please review the California Urban and Community Forestry Inflation Reduction Act 2024 Grant Guidelines for further guidance on specific program requirements.

## Allowable Costs

A cost is allowable if it directly relates to the approved project and is incurred solely to advance work under the Grant Agreement. Allowable costs may include salaries and wages, fringe benefits, consultant services, travel, subcontractors and materials, data collection and analysis, land or equipment rentals, and training.

Expenditures must conform to the USDA Forest Service and CAL FIRE UCF Program requirements, be made in compliance with federal and state laws and regulations as applicable, and be:

- Necessary and reasonable for proper and efficient performance and administration of the project.

- Authorized or not prohibited under federal, state, or local laws or regulations.

- Consistent with policies, regulations, and procedures that apply uniformly to both federal and state funds and other activities of the governmental unit.

- Determined in accordance with generally accepted accounting principles.

- Adequately documented.

## Unallowable Costs

A cost is unallowable if it does not comply with applicable cost principles, program requirements, or other terms and conditions of the Grant Agreement. A cost is also unallowable if it is not contained in the approved scope of work or is not necessary and reasonable to advance the work of the project.

Unallowable costs will not be reimbursed.

Specific expenses that are unallowable include, but are not limited to, land acquisition, equipment (as defined in the CFR), decorative tree grates and tree guards, inefficient irrigation valves, pumps, and sprinkler control timers or overly costly irrigation systems or irrigation systems that prove to be ineffective in the long-term, root barriers (unless approved by CAL FIRE Regional Urban forester), trees that require excessive amounts of water to survive, trees inappropriate for the chosen site as determined by CAL FIRE, trees of a stock size other than 15-gallons without prior approval from CAL FIRE, trees that will be less than 25 feet in height with equal crown width at maturity, palm trees, invasive tree and plant species, food (unless as part of approved per diem travel expense), refreshments, gifts, donations, and other items not directly related/required to implement the project, promotional materials or other supplies unnecessary for carrying out the operations of the project aside from education and outreach, tree inventories that are not assessing or working towards assessing the entire urban forest resource within the jurisdiction, playground structures for schoolyard greening projects, tree removal (unless otherwise necessary for the project and approved by the CAL FIRE Regional Urban Forester)

Additional guidance regarding allowable and unallowable costs and activities is available from the assigned Forester as well as the California Urban and Community Forestry Inflation Reduction Act Grant Guidelines.

## Direct and Indirect Costs

### Indirect Cost Rate

Indirect costs are limited to a de minimis rate of 10% of the Modified Total Direct Costs (MTDC), unless the grantee has an approved Negotiated Indirect Cost Rate Agreement (NICRA) with the federal government. The MTDC includes all direct salaries and wages, applicable fringe benefits, materials and supplies, services, travel, and up to $25,000 of each sub-award or contract. MTDC excludes equipment, capital expenditures, rental costs, tuition remission, scholarships and fellowships, participant support costs, and the portion of each subaward in excess of $25,000.

### Charging Direct and Indirect Costs Consistently

Recipients are prohibited from charging an indirect cost as a direct cost. Recipients are responsible for presenting costs incurred for the same purpose in like circumstances consistently and must not include costs associated with their organization’s indirect cost policy as direct costs.

Direct costs are costs that can be identified specifically with a particular project or can be directly assigned to a project activity relatively easily with a high degree of accuracy.

Typically, direct costs include, but are not limited to, compensation for employees who work directly on the project, travel, and supplies necessary to the project.

Indirect costs (also known as “facilities and administrative costs”) are costs incurred for a common or joint objective that cannot be identified specifically with a particular project. Typically, indirect costs include, but are not limited to, compensation for executive officers, and administrative and clerical staff, costs of operating and maintaining facilities, general administration expenses (such as supplies that cannot be identified specifically with a particular project), accounting and personnel services, depreciation, and insurance.

The salaries of administrative and clerical staff should normally be treated as indirect costs. However, direct charging of these costs may be appropriate where all of the following conditions are met:

- Administrative or clerical services are integral to the project or activity;

- Costs involved can be specifically identified with the project or activity;

- Such costs are explicitly included in the approved budget; and,

- The costs are not also recovered as indirect costs.

All criteria above must be met before a determination can be made whether the costs are allowable as direct costs. Approval must also be obtained from the CAL FIRE UCF Program. Compliance with other requirements, such as timekeeping requirements, must also be met.

The following are considered indirect and should not be charged to the grant as direct costs:

  - Information technology services

  - Rent

  - Utilities and internet service

  - Telephone service (mobile and land-line)

  - General office supplies

  - Insurance and indemnification

## Scope of Work Revisions

Scope of Work (SOW) revisions are required when changes to activities, milestones, dates, deliverables, support from other grant programs, and/or budget occur. Requests for revisions must be made in writing and provide sufficient information to explain the need and how the change affects the project. Revisions must be requested by an authorized official of the Recipient organization, and approved by the CAL FIRE UCF Program, and in some instances the USDA Forest Service. Reimbursement is available only for approved project activities.

Failure to obtain prior approval of SOW revisions may result in costs being deemed unallowable, request for reimbursement denied, and may result in audit findings.

Examples of project changes that require a SOW revision include, but are not limited to:

  - Changes within the budget line items (addition, deletion, or revision of personnel, contractors/consultants, travel, supplies, etc.).

  - Transfer of project work to a third party through a contract, sub-grant, or any other means.

  - The addition, deletion, or revision of activities and/or deliverables.

  - Change of Recipient, Recipient organization name, or Recipient organizational status.

  - Changes to the goals or sub-goals.

  - The Recipient receives grant funds to support similar project costs/activities from another federal or state grant program.

  - The Recipient receives federal or state assistance to support costs that are also supported with UCF IRA grant funds.

Consult with the assigned Forester for further instructions on completing a SOW revision.

## Line Item Shift Requests

In the event a change to the project’s budget line items is necessary, Recipients are required to complete and submit to the CAL FIRE UCF Program a SOW revision along with a Line Item Shift Request (LISR) in advance to adjust budget line items. Approval for the LISR must be obtained from CAL FIRE prior to incurring costs under the revised budget.

The following restrictions and requirements apply to LISRs:

  - The project award amount cannot be increased or decreased through this process.

  - Any primary budget line-item increase or decrease by 10% or more of that line-item during the grant period will require a formal grant amendment.

  - Minor changes or modifications to budget line-items (>10%) can typically be approved by the Grant Manager or Regional Urban Forester.

  - The amount of indirect cost allowed may need to be altered based on changes to each budget category.

  - LISRs must be accompanied by a SOW revision.

Note: Recipients may have multiple LISRs throughout the Agreement Term.

## Notification of Problems and Delays

Recipients must immediately notify the assigned Forester of any delays, problems, and/or adverse conditions that may materially affect the project. Some problems and delays may require a SOW revision. Examples include but are not limited to:

  - Inability to complete any activity according to the work plan or work plan schedule;

  - Challenges quantifying or activities related to the expected goals and subgoals;

  - Challenges or inability to fill vacant positions resulting in activities being delayed or eliminated; and/or

  - Delays meeting required due dates for invoices, progress reports, or the final report.

## Program Income

Program income is earned by the Recipient from activities supported by or as a result of the grant. The use of program income for the UCF IRA grant is based on the Deduction method (reference 2 CFR 200.307(e)(1)). The Deduction method will be applied by reducing an invoice by the amount of program income earned during the reporting period.

Recipients are prohibited from retaining program income as profit or funding for the Recipient. Program income may not be used to support unallowable costs or activities. Program income should be expended prior to federal grant funds. To comply with this expectation, Recipients should use program income as soon as reasonably possible for grant related activities.

If there are unused program income funds at the end of the grant, the Deduction method will be applied by reducing the final invoice by the amount of program income left unspent. If the final reimbursement invoice is less than the amount of unspent program income, then the Recipient must remit to CAL FIRE the unused portion of program income in the form of a check made payable to the “California Department of Forestry and Fire Protection” and mailed to Cashier, Department of Forestry and Fire Protection, PO Box 944246 Sacramento, CA 94244-2460. Please note the Grant Agreement number on the check.

Program income is reported on invoices, progress reports, and final reports. Reporting on progress and final reports includes the nature or source of the program income (e.g., registration fees), the amount, and a description of how the program income was used. The Recipient must track program income generated and its use and make this information available upon request by the CAL FIRE UCF Program. In addition, program income is subject to a financial compliance audit to ensure funds are being used for the intended purpose in compliance with federal cost principles and the Grant Agreement.

Changes to the use of program income require prior approval through a SOW revision.

## Cost Share

Cost share refers to matching funds and/or in-kind contributions. Cost share is not required for UCF IRA grants, however, any activities/expenses being reported as cost share must be tracked and used for allowable activities as outlined by CFR. The Recipient must notify the assigned Forester if the amount or activities covered by cost share has changed.

Cost share is reported on invoices, progress reports, and final reports. Reporting on progress and final reports includes the type of cost share (i.e., matching funds or in-kind contributions) and the amount.

## Timekeeping Requirements

Activity reports are required to support salary and wage and fringe benefit expenditures charged to UCF IRA grants. Each report must account for the total activity for which each employee is compensated, as well as the hours worked on a particular UCF IRA grant project. A description of activities must be included, and the description must include enough detail to determine whether the activity is project related. This also applies to salaried employees, such as Executive Directors (reference 2 CFR 200.430). Costs not adequately supported are unallowable and will not be reimbursed

Fringe benefits must be billed at or below actual cost in accordance with the Recipient’s established fringe benefits policy; billing fringe benefits based on estimated rates is unallowable.

## Travel

All travel costs must be substantiated by receipts. Costs not substantiated by receipts are considered unallowable and will not be reimbursed. Credit card statements are not acceptable as receipts to support travel costs.

Prior approval is required for domestic travel. Please see Prior Approval Required on page 2 and Scope of Work Revisions on page 5.

### Domestic Tavel

Reimbursement is for actual costs up to the maximum allowance for meals, incidentals, and lodging expenses for each complete 24 hours of travel. The maximum travel rates allowable are the lesser of the rates in effect at the time of travel as established by the United States (U.S.) General Services Administration (GSA), or the Recipient’s established travel policy.

Luxury accommodations include lodging at all-inclusive hotels/resorts or multi-bedroom suites are never appropriate using federal funds. Luxury accommodations or other forms of lodging that exceed the GSA rate, even when travel involves multiple individuals sharing a single accommodation such as a suite, are unallowable.

### Ground Transportation

#### Privately Owned Vehicle

Mileage reimbursement for using a privately owned vehicle will be at the standard mileage rate established by the U.S. Internal Revenue Service (IRS) in effect at the time of travel. Mileage logs should be utilized to substantiate mileage costs.

#### Rental Vehicle

Recipients should utilize the most economical rental vehicle option available. Reimbursement is up to the actual cost. Excessive costs will be disallowed and/or reduced to a reasonable, allowable rate. The cost for a rental vehicle will only be reimbursed for travel related to the project and will not be reimbursed to accommodate any personal travel. In cases where there is a need for another type of vehicle (such as several people traveling together with luggage or carrying equipment), the Recipient must provide a justification to the UCF IRA Program staff.

Fuel reimbursement when using a rental vehicle will be at the actual cost for the fuel and must be supported with receipts. Recipients will not be reimbursed the standard mileage rate established by the IRS for a rental vehicle.

#### Rideshare Service

Recipients should utilize the most economical rideshare service (e.g., Uber, Lyft, taxicab) option available. Reimbursement will be at the actual cost and must be supported with receipts.

Note: Travel by a luxury vehicle such as a limousine is never appropriate using federal funds and will not be reimbursed.

### Parking

Recipients should utilize the most economical parking option available. Reimbursement for parking is up to the actual cost and must be supported with receipts. Excessive costs will be disallowed and/or reduced to a reasonable, allowable rate.

### Air Travel

All travelers must use economy-based rates for airfare. Reimbursement is available up to the actual airfare expenses incurred and must be supported with receipts. The following costs related to air travel are unallowable and will not be reimbursed:

  - Upgraded seats

  - Priority boarding

  - Excessive booking fees

  - Seat assignment fees

## Contractors/Consultants

Recipients may contract for services that cannot be provided by staff employed by the Recipient. Generally, these services are for a short-term period and provide a specific and identifiable product or service. Recipients are responsible for ensuring their contractors/consultants comply with applicable federal regulations and requirements. Contracting out must not affect the Recipient’s overall responsibility for the management of the project, and the Recipient must reserve sufficient rights and controls to enable it to fulfill its responsibilities for the project.

Recipients must establish and follow a documented procurement policy which conforms to applicable federal law and reflects applicable state, local and tribal laws and regulations. Reference 2 CFR 200.318 for additional information on general procurement standards.

Prior approval is required when contracting out or obtaining the services of a third party. Please see Prior Approval Required on page 2 and Scope of Work Revisions on page 5.

### Competitive Process

Federal regulations require all procurement transactions be conducted in a manner providing full and open competition and consistent with the procurement standards of 2 CFR 200.317 – 200.327.

### Noncompetitive Procurement

There are specific circumstances in which noncompetitive procurement can be used. Noncompetitive procurement can only be awarded if one or more of the following circumstances apply:

(1) The aggregate amount of the procurement transaction does not exceed the micro-purchase threshold ($10,000);

(2) The procurement transaction can only be fulfilled by a single source;

(3) The public exigency or emergency for the requirement will not permit a delay resulting from providing public notice of a competitive solicitation;

(4) The Federal awarding agency or pass-through entity expressly authorizes a noncompetitive procurement in response to a written request from the non-Federal entity; or

(5) After soliciting several sources, competition is determined inadequate.

### Written Agreement

The Recipient must have a written agreement with each contractor/consultant. The written agreement must include at a minimum: beginning and ending dates, dollar amount of the contract, a description of activities, services or deliverables to be performed with a time schedule, a budget, the cost principles to be used in determining allowable costs (as noted in the Compliance with Federal Requirements, page 3), payment provisions, the policies and requirements that apply to the contractor/consultant (including those required by Appendix II to 2 CFR 200), and signature and date by both the Recipient and the contractor/consultant. An amendment to the contract between the Recipient and the contractor/consultant is required if there are changes to the contract such as the budget, payment provisions, services provided, etc. Amendments require a signature and date by both the Recipient and the contractor/consultant. Lastly, the budget in the contract must include the same line-item categories as the Grant Agreement budget (e.g., flat rate, personnel, fringe, etc.).

### Compensation

Contractor/consultant invoices provided to the Recipient must include sufficient detail and information to determine that the expenditures invoiced are project related, reasonable and allowable.

Contractors/consultants must comply with federal requirements regarding timekeeping. Hourly or salaried compensation (including hourly rates for “Professional Services”) for contractors/consultants may not exceed fair market price (you may reference the GS-15 step 10 for the Recipient’s locality as a guideline) unless a justification is provided and approved by CAL FIRE UCF staff.

Compensation based on a flat-rate for services requires pre-approval from CAL FIRE UCF. When utilizing a flat-rate for services, Recipients must include a justification for the flat-rate fee and demonstrate the rate is reasonable and consistent with fees in the marketplace for similar services. The inclusion of costs that would otherwise be unallowable within a flat-rate for services is prohibited.

The rate and method of compensation (e.g., salary and fringe, flat rate, etc.) must match the SOW as well as the written agreement between the Recipient and the contractor/consultant. A SOW revision is necessary if the rate and/or method of compensation changes from the approved SOW.

#### Justification for Compensation Exceeding Fair Market Price

Compensation for contractors/consultants may not exceed fair market price unless one of the following is provided to and approved by CAL FIRE UCF:

- A description of the steps taken to hire a contractor, which includes obtaining and providing a cost/price analysis (i.e., a quote or bid) from at least three contractors who can perform the service. The purpose of the cost analysis is to review and evaluate each element of cost to determine reasonableness; or

- Due to the complexity or uniqueness of the project, the pool of available and qualified contractors is limited. The unique qualifications of the contractor and a justification regarding why those unique qualifications and proposed contractor are required for the project must be provided. The justification must include a description of the steps taken to hire a contractor and how the determination was made that the pool of available and qualified contractors is limited.

Note: The GS-15 step 10 is a salary table and the rate listed does not include fringe benefits, travel, indirect costs or other expenses.

Note: Procurement through a competitive process does not constitute an approved justification for exceeding the fair market price; conversely, approval of a rate exceeding the fair market prices does not eliminate the requirement to conduct a competitive procurement process.

#### Indirect Costs for Contractors/Consultants

Indirect costs for contractors/consultants are allowed. The indirect cost rate cannot exceed the maximum allowable (see Indirect Cost Rate, page 4).

### Contractor/Consultant Invoices

The Recipient must obtain and maintain all contractor/consultant invoices and make them available to CAL FIRE upon request. Contractor/consultant invoices must contain the following information:

  - Contractor/consultant organization/name;

  - Period of performance for the billing and date(s) the actual work was performed;

  - Rate and method of compensation (e.g., hourly rate, flat rate, etc.); and

  - A description of services and/or deliverables performed for the billing period.

Note: Compensation for the Recipient’s contractors/consultants should be in compliance with the executed agreement between the Recipient and the contractor/consultant.

## Equipment

Equipment is tangible, nonexpendable, personal property having a useful life of more than one year and an acquisition cost of $5,000 or more per unit. Equipment purchases are not an allowable expense under this grant.

## Publicity and Acknowledgment

### Publicity

Recipients must notify CAL FIRE in writing at least two working days before any news/press releases or public conferences are initiated by the Recipient or its contractors relating to the project and any project results.

All grant projects shall also have one or both of the following forms of public recognition:

- At least one project sign at highly visible project locations that must:

  - Be on site for at least three years after a project is complete; and

  - Be approved by CAL FIRE staff prior to purchase or use to ensure usage requirements are met; and

  - Include the funding source that is funding the grant as well as the names and/or logos of all the project cooperating entities, including CAL FIRE and the USDA Forest Service.

- Recognition of the funding source and the names and/or logos of all project cooperating entities, including CAL FIRE and the USDA Forest Service in all publications, websites, electronic media, products paid for by the grant, etc.

### Acknowledgment of Support

In addition to the inclusion of logos, all signage and/or forms of recognition should include the following text:

“Funding for this Project was provided by the USDA Forest Service Urban and Community Forest Program via the Inflation Reduction Act, as administered by the California Department of Forestry and Fire Protection (CAL FIRE) Urban and Community Forestry Program.”

### Logo Usage

#### CAL FIRE Logo

Recipients must use the CAL FIRE logo for project signage and development of communications products for 2024 Inflation Reduction Act projects.    Please refer to the  California IRA Project Logo and Signage Approval Guidance document for CAL FIRE logo use guidelines.

#### USDA/U.S. Forest Service Logo

Recipients must use the USDA Forest Service insignia for project signage and development of communication products for 2024 Inflation Reduction Act projects.  Approval to use Forest Service insignia art is required. Use of the insignia is protected by Title 36 Code of Federal Regulations 264.1 – 264.5. See your CAL FIRE grant administrator for details on how to get approval to use the insignia.  Please refer to the California IRA Project Logo and Signage Approval Guidance document for USDA Forest Service insignia use guidelines.

#### Rights in Intellectual Property.

Grantee retains title to all data, plans, drawings, specifications, reports, computer programs, operating manuals, notes, other written or graphic work, or patentable ideas (collectively, “Intellectual Property”) produced in the performance of this Agreement, except that the State shall have the right to reproduce, publish, sublicense, and use all such work, or any part thereof, in any manner and for any non-profit, noncommercial purposes and to authorize others to do so. If any Intellectual Property is copyrightable, Grantee may copyright the same, except that the State reserves a royalty-free, nonexclusive, and irrevocable license to reproduce, publish, sublicense, and use such work, or any part thereof, in any manner and for any non-profit, noncommercial purposes and to authorize others to do so.

#### Photographs and videos.

Recipients shall ensure that any person depicted in photographs and/or videos submitted to CAL FIRE have each signed a written waiver authorizing CAL FIRE to use their photographic or video image(s) for any non-profit, non-commercial purpose in its web site, newsletter, or any other publication, and that CAL FIRE may distribute the image to newspapers, television, or other media for use in news stories pertaining to CAL FIRE. If the person whose image is depicted in the photograph or video is under the age of 18, the authorization must be signed by a parent or guardian.

## Payment Methods

There are two payment methods for allowable costs incurred – advance payments and reimbursement payments. It may take up to 45 days from the date the invoice or advance payment request is received for a check to be issued by the California State Controller’s Office on behalf of CAL FIRE. If invoices are returned to the Recipient for correction or amendment after they are initially submitted to CAL FIRE, then it may take longer than 45 days from the original submittal date to receive a check from the California State Controller’s Office on behalf of CAL FIRE.

### Advance Payments

As of July 2025, Advance Payments are not allowable until further notice.

Recipients may be eligible to receive an advance payment to cover anticipated project expenditures. Written approval must be given by the CAL FIRE grant administrator prior to submitting an advance payment request. Advance payments may not exceed five percent or up to $50,000 of the total award and must be fully utilized within a 90-day period unless additional time is approved by CAL FIRE. Advance payment is not allowable under the following circumstances:

- an existing advance is not completely liquidated;

  - the advance will reduce the project balance below 10 percent of the award amount;

  - there is an invoice dispute;

  - there is a pending resolution of an audit or desk review finding of overpayment, unallowable costs, inadequately supported, or unsupported costs;

  - the project is not current in invoicing or reporting;

  - the project is in the final three months of the project duration; and/or

  - additional conditions imposed prohibit an advance payment.

#### Advance Payment Request Procedures.

To ensure timely processing of an Advance Payment Request, the Recipient must do the following:

  - Estimate the advance amount needed for up to a three-month period;

  - Submit an Advance Payment Expenditure Plan and;

  - Submit an Advance Payment Request and Accountability Report accompanied by an Advance Payment invoice to CAL FIRE

The California State Controller’s Office issues advance payment checks. Upon receipt, funds must be deposited into a federally insured, interest-bearing account that provides the ability to track interest earned and withdrawals.

The Recipient must minimize the time elapsing between receipt of the advance payment funds and disbursement of the advance payment funds.

Interest earned during a six-month period must be remitted to CAL FIRE, in the form of a check made payable to the “California Department of Forestry and Fire Protection” and mailed to Cashier, Department of Forestry and Fire Protection, PO Box 944246 Sacramento, CA 94244-2460. Please note the Grant Agreement number on the check.

### Reimbursement Payments

Recipients submit invoices to CAL FIRE for reimbursement of actual expenditures incurred. Invoices must be submitted monthly until further notice, unless instructed otherwise by the CAL FIRE grant administrator.

## Invoices

Grantees shall report and invoice on all projects quarterly, unless notified otherwise by the CAL FIRE grant administrator. The reporting dates shall be for the periods ending March 31, June 30, September 30, and December 31. Invoices and reports are due within 30 days after each reporting period. Invoices shall not be submitted more frequently than monthly, and progress report periods shall not overlap. Final invoices are due no later than 30 days following the expiration of the Grant Agreement term or after the project is complete, whichever comes first.

### Completing an Invoice

Reimbursement Invoice.

Recipient completes the Invoice Reporting Period, Grant Period, Grantee Contact Information, Invoice Submission Date, Budgeted Amount, Current Costs, Expended to Date, and Current Match columns. Grantee also indicates invoice attachments in “Check all those that apply” section including:

- Supporting documentation attached (required for Interim & Final Payments)

- Project Progress Report (required for Interim Payments) or Project Completion Report (required for Final Payment)

- Minimum Data Collection Attributes (MDCA) (Online Hub submission required for Interim Payments that include planting expenses)

- USDA Forest Service Biannual Accomplishments Report (due every six months by June 30th and December 31st)

- CA Air Resources Board Job Benefits Modeling Tool (only required for Final Report and Payment)

- CA Air Resources Board Greenhouse Gas (GHG) Benefits Calculator Tool (only required for Final Report and Payment)

Grantees must complete Payment Tracker to track total project expenses.

If seeking compensation for salaries and/or mileage reimbursement, grantees must complete Salaries and Wages and Mileage sections of invoice request template.

- As of July 2025, the federal mileage reimbursement rate is $.70 per mile. Mileage rates charged shall not exceed the rates allowable by IRS via Standard Mileage Rates.

Grantee certifies that the information is correct with an authorized representative’s name, phone number, email, and date. Recipient then submits the invoice via eCivis for review and processing.

Advance Payment Liquidation Invoice.

Recipient follows the instructions for a Reimbursement Invoice. The invoice template automatically calculates the amount to be paid, less the advance payment.

Final Invoice.

Recipient follows the instructions for a Reimbursement Invoice and marks the invoice as “Final Payment” indicating all payment obligations have been met and no further payments are due.

### Supporting Documentation

Recipients must collect and maintain source documentation associated with costs incurred as a result of the Grant Agreement and make it available to CAL FIRE upon  request. Source documentation includes, but is not limited to, receipts, canceled checks, paid bills, payroll, time and attendance records, contracts, invoices, and subaward documents. If recipients pay a portion of the total amount indicated on the source document, it must appropriately identify the specific expenses and total amount charged to the grant.

Supporting documentation must be submitted to CAL FIRE with each invoice with expenditures to ensure compliance with the Grant Agreement.

# Reporting Requirements

## Progress and Final Reports

CAL FIRE may require grantees to submit an additional, more detailed Biannual Accomplishment Reports required by the USDA Forest Service every six months (on June 30th and December 31st through grant expiration date) to meet federal Inflation Reduction Act reporting requirements. Grantees may request a grant modification or amendment if additional progress reporting requires additional resources or staff time.

### Progress Reports

Invoices

- Grant funds expended for the reporting period and to date for the grant.

- Total funds expended for the reporting period and to date for the grant.

- Match funds reported for the reporting period and to date for the grant.

Summary of Activities

- A general description of activities, events, or milestones completed during the reporting period.

- Any planned events or milestones expected for the next reporting period.

- A description of any challenges faced and if the challenges were overcome.

- Planned events and future planned activities or milestones.

Partnerships

- A description of the role of project partners during the reporting period and any challenges or successes derived from the partnerships.

Priority Populations

- A list of the disadvantaged and/or low-income census tracts worked within the reporting period.

Planting and Maintenance Activities

- For any tree or plant planting activity, grantees must submit a Minimum Data Collection Attribute (MDCA) spreadsheet. This spreadsheet must be submitted via the Online Submission App accessed via the Urban and Community Forestry Hub Site

  - You must be signed into your Hub Community account to see the Project Data Submission page link where you will find the app.

  - For technical support with uploading data to the MDCA Data Online Submission App contact:

    - Francesca Rohr

    - GIS Specialist, CAL FIRE Urban and Community Forestry Program

    - Francesca.Rohr@fire.ca.gov and urbanforestrygis@fire.ca.gov

    - Cell Phone: 916 926-2844

- The number of trees planted in the reporting period and to date for the grant, and/or any other plants planted in the reporting period and to date for the grant.

- Minimum Data Collection Attributes Spreadsheet (MDCA) will be provided to grantee. MDCA tree data to be reported for each reporting period and the project to date includes:

  - Unique tree number identifier, tree funder, scientific name, street address, other location information, city or urban area, ownership type, latitude, and longitude (x/y coordinates), census tract, priority population (DAC/LIC) status, date planted, tree stock size, and the type of growing space.

- A description of all tree and plant maintenance activity completed during the reporting period.

Community Outreach and Engagement

- Describe community engagement efforts, including outreach, educational events, trainings, open houses, workshops, and meetings. Specify which, if any, were focused on youth engagement.

- Describe travel and training events, including conferences, meetings, and trainings.

- Describe progress towards educational / outreach products created, including number completed and distributed.

Workforce Development

- Indicate the total number of youth (17 and under) participants to date

- What kind of training program was this youth project? Select all that apply.

- Indicate the total number of adult (18 and over) participants to date

- What kind of training program was this adult project? Select all that apply.

- Please enter the number of adults who earned each of the credential types listed. If no adults earned a credential type, leave the value as 0.

- Indicate the type skills or work experience that Workforce Development (both youth and adult) participants acquired. Select all that apply.

- Please enter the number of graduates (both youth and adult) employed by each job type listed.

Volunteer Activities

- Number of volunteers engaged

- Number of volunteer hours logged

Project Co-Benefits

- Improved air quality, public health, urban forest management, water quality, stormwater reduction, reduced urban heat island (UHI) effects, job creation and/or training for residents of a priority population, urban forests job creation and job training, community engagement with planting and/or maintenance, long term access to nature and natural shade, outdoor classrooms, improved collaborative play and social development of students, increased environmental literacy, food production, staff training, educational materials/media products, wildlife habitat.

- Net Greenhouse Gas benefits (metric tons of CO2e) using the CA Air Resources Board GHG Benefits Calculator is required upon submission of the final report during grant close-out.

Grant Products

- Include a description of phases, reports, or assessments completed. Include a short description of the tool and what phase of development it is in.

- Describe progress on any management planning, assessment development, articles, or product blueprints

- Describe progress on any inventory, monitoring, and assessment tools

- Representative project photos and/or maps.

- Grant products produced (ex: educational materials, event fliers, meeting attendance sheets, reports, etc.)

Green Schoolyards Temperature Recordings

- CAL FIRE Green Schoolyards app for recording temperatures and photos on campus. This app is accessed via the ArcGIS Survey123 app on your mobile device using your unique Urban and Community Forestry Hub Site account login username and password.

- Please see ‘Instructions for Using CAL FIRE Green Schoolyards Survey123 App’ PDF for more information.

Project Challenges

- Please include any obstacles that have presented challenges during the implementation of your project.

Planned Events and Milestones

- Please spotlight any upcoming events that CAL FIRE could amplify through leadership attendance or official public communication pathways. Include hyperlinks or attachments for relevant events, if applicable.

Photographs, Videos, and Other Attachments

- Please provide any photos or videos related to the project, and please specify if photos and videos can be shared and published by CAL FIRE and USDA Forest Service. Only photos and videos with this approval will be used publicly. Include descriptive captions with locations, dates, and photo credits (photographer name, association/organization name).  Photos and videos should be uploaded to eCivis as pdfs. Please provide links or attachments to any products created as part of this project or articles from the press about the project. Attachments should be uploaded to eCivis as pdfs.

Financial Projections

- Please submit a detailed projection of how expenses will be spent if the remaining budget is greater than 15 percent of the total award amount six months prior to the project’s completion date (October 1, 2027).

- Please report any estimated unused funds three months prior to the project’s completion date (March 31, 2028).

## Remaining Funds Reporting

### Six Months Prior to Project Completion

Recipients are required to submit a detailed projection of how expenses will be spent if the remaining budget is greater than 15 percent of the total award amount six months prior to the project’s completion date.

### Three Months Prior to Project Completion

Recipients are required to report any estimated unused funds three months prior to the project’s completion date.

Note: There is no penalty to Recipients for having remaining funds at the end of the agreement; CAL FIRE requests this information for budgeting purposes only.

## Single Audit Requirements

State, local, and tribal governments, non-profit organizations, and institutions of higher education that expend more than $750,000 annually in federal awards must comply with the single audit requirements contained in 2 CFR 200 Subpart F, and are required to submit a copy of the single audit report to CAL FIRE.

# Compliance and Remedies for Noncompliance

## Compliance Reviews

All Grant Agreements are subject to a minimum of one performance site visit, as well as a financial compliance audit, desk review and/or Agreed Upon Procedure (AUP). The purpose of compliance reviews is to determine whether project deliverables are being met, evaluate accomplishments, and to review financial records and documentation to ensure funds are being used for the intended purpose in compliance with federal cost principles, the Grant Agreement terms and conditions, and the GMP.

Site visits, audits, desk reviews and AUPs are generally conducted during the term of the Grant Agreement but may be conducted up to three years after the Grant Agreement has ended. Recipients must allow access to records and documentation relevant to the Grant Agreement, as well as any employees who may reasonably have information related to the Grant Agreement.

Recipients may be required to submit supporting documentation for an invoice for a desk review or AUP. Documentation may include but is not limited to timesheets and payroll records, travel logs that document mileage, invoices/receipts for costs incurred, lodging, and meals, and contractor/consultant contracts and invoices.

A Grant Analyst will contact the Recipient to schedule a performance site visit and/or desk review. An authorized representative of CAL FIRE, such as a CAL FIRE auditor, will contact the Recipient to request supporting documentation for an AUP and/or to schedule an audit.

All project records must be retained by the Grantee for a period of not less than one year after the State audit or after the final disposition of any disputed audit findings. Record retention and accessibility is governed by 2 CFR 200.334

## Remedies for Noncompliance

Pursuant to 2 CFR 200.339, CAL FIRE may take one or more of the following remedies for failure to comply with federal and state laws and regulations, Grant Agreement terms and conditions, and/or the GMP:

  - Disallowance of costs for all or part of the cost of the activity or action not in compliance, or for the invoicing or reporting period not in compliance;

  - Withdrawal of authorized personnel approval;

  - Withholding of payments;

  - Denial of advance payment requests;

  - Imposition of additional conditions; and,

  - Suspension or termination of the Grant Agreement.

### Additional Conditions

Pursuant to 2 CFR 200.208, CAL FIRE may impose additional specific conditions on Recipients that have been identified as high risk or are noncompliant with federal and state laws and regulations, Grant Agreement terms and conditions, and/or the GMP.

Reasons for imposing additional conditions include but are not limited to:

  - Late invoices or progress reports;

  - Audit, desk review, or AUP findings;

  - History of unsatisfactory performance; and/or

  - Noncompliance with terms and conditions of current or previous UCF awards. Additional condition examples include but are not limited to:

  - More frequent submission of progress reports;

  - More frequent submission of invoices;

  - Submission of supporting documents with each invoice;

  - Additional site visits, audits, desk reviews, and/or AUPs;

  - Requiring payments as reimbursements rather than advance payments; and/or

  - Establishing additional prior approvals.

Recipients will be notified in writing of the additional conditions imposed; the reasons for imposing the additional conditions; the actions required, if any, to remove the additional conditions; the timeframe in which the required actions must be completed; and the method of appealing the additional conditions imposed.

### Termination of Grant Agreement

Pursuant to 2 CFR 200.339 – 200.341, CAL FIRE may terminate a Grant Agreement for noncompliance. The Recipient will be notified in writing of the reasons for termination, the date the termination is effective, and the method for appealing the termination.

### Loss of Funding

The following are examples of actions that may result in a Grantee’s loss of funding:

- Grantee fails to provide direct, meaningful, and assured benefits to a disadvantaged community or low-income community per criteria in CARB Funding Guidelines when such status is claimed.

- Grantee withdraws from the grant program.

- Grantee fails to complete the funded project scope of work within the grant period.

- Grantee fails to submit all documentation within the time periods specified in the Grant Agreement.

- Grantee fails to submit evidence of California Environmental Quality Act (CEQA) compliance within one year of the execution of the grant agreement.

- Grantee changes the project scope or budget without concurrence of the State.

- GHG reductions fail to be achieved by the project when such reductions are claimed.

- Grantee exercises poor communication or responsiveness, jeopardizing CAL FIRE’s assurance that project objectives are being met or that CAL FIRE direction is being followed.

- Grantee fails to comply with the terms of the grant agreement unless such failure was due to no fault of the grantee. Such a determination will be made solely by CAL FIRE.

# Closeout

Before the Grant Agreement is closed, CAL FIRE will review the final report and invoice, and verify resolution of any project performance concerns or compliance audit findings. A closeout letter and final payment will be issued when closeout review is completed.

Closeout does not cancel property management, record retention, or financial accountability requirements.

## Property Management and Disposition

### Intellectual Property

Intellectual property includes, but is not limited to: inventions, patents, digital and physical media, created as a result of CAL FIRE UCF IRA funding. Recipients retain title to any inventions, patents, digital and physical material conceived or developed using CAL FIRE UCF IRA  funds with the following conditions:

  - Recipients must promptly disclose CAL FIRE UCF IRA funded inventions to CAL FIRE. The disclosure should be sufficiently complete in technical detail to convey a clear understanding, to the extent known at the time of disclosure, of the purpose, nature, and operation.

  - Recipient must formally grant the federal government and CAL FIRE a limited use license to any inventions.

  - Recipient must provide the federal government and CAL FIRE a royalty-free, non-exclusive, and irrevocable license to reproduce, publish, or otherwise use the material, and agrees that the federal government and CAL FIRE may do so in cooperation with other public agencies.

### Special Purpose Equipment

The purchase, use, management, maintenance, disposition, and reporting of special purpose equipment purchased with or developed under a Grant Agreement is governed by the property standards contained in 2 CFR 200.310 – 200.316. It is important to note these requirements remain in effect after the close of the Grant Agreement.

## Record Retention

Record retention and accessibility is governed by 2 CFR 200.334 and 2 CFR 200.337.

Recipient must retain financial records, project records, and supporting documents until April 30, 2031 or until any litigation related to the grant is resolved, whichever is later. All records must be made available to CAL FIRE or its designees upon request.

Records that must be retained include:

- Timesheets and records that reflect the total activity (including descriptions) for which each employee is compensated;

- Actual expenditure invoices of direct costs charged to grant funds;

- Employee reimbursement claims including lodging, per diem, and transportation receipts;

- Documentation supporting calculation or methodology to determine indirect costs; and,

- All other supporting documentation related to the Grant Agreement.